## Slide 1
INDIAN TRAIL COMPLETE STREET
JUNE 12, 2025

## Slide 2
IT COMPLETE STREET PHASE 1
www.indiantrail.org
DISCUSSION ITEMS:
Project Update
Amendments to CIP Ordinance

## Slide 3
PROJECT UPDATE
www.indiantrail.org
CURRENT ACTIVITIES:
NCDOT Submittals
Water and Sewer Plans
Utility Coordination w/ Third-Party Providers

## Slide 4
NCDOT SUBMITTALS
www.indiantrail.org
R/W Certification
R/W Reimbursement
Construction Authorization

## Slide 6
WATER AND SEWER PLANS
www.indiantrail.org
County finished final review
Address minor comments
Submit to NCDOT

## Slide 10
IT COMPLETE STREET PH 1
www.indiantrail.org
Union County Water and Sewer Design:
County Portion = $1,500,000.00
Town Portion = $500,000.00 (reimbursable)
        TOTAL = $2,000,000.00
        Note: County pays 100% for their portion.

## Slide 11
THIRD-PARTY UTILITIES
www.indiantrail.org
Follow Up Coordination Meetings
Finalizing one design
Conduit Count and Color Scheme

## Slide 13
AMENDMENT TO ORDINANCE
www.indiantrail.org
UTILITIZE THE REST OF SCIF GRANT FUNDS FOR THE FOLLOWING:
Design Coordination
R/W Acquisition
Construction/Betterments

## Slide 14
DESIGN COORDINATION
www.indiantrail.org
Roadway Design (EC, Stormwater, Traffic, Paving, Etc.)
Signal Design
Utility Design
UBO Coordination

## Slide 15
R/W ACQUISITION
www.indiantrail.org
CURRENT R/W FUND = $2,500,000.00
FUNDS NEEDED = $53,000.00+
RECENT ACQUISITION = $30,000.00
ADDITIONAL FUND REQUEST = $100,000.00

## Slide 16
CONDEMNATION UPDATES
www.indiantrail.org
No. | PARCEL NUMBERS | STATUS OF CONDEMNATION
1 | PARCEL 5 | COMPLAINT FILED, MEDIATION TO OCCUR NEXT
2 | PARCEL 6 | COMPLAINT FILED, MEDIATION TO OCCUR NEXT
3 | PARCEL 7,47 | COMPLAINT FILED, MEDIATION TO OCCUR NEXT
4 | PARCEL 18 | COMPLAINT FILED, MEDIATION TO OCCUR NEXT
5 | PARCEL 24,45 | COMPLAINT FILED, MEDIATION TO OCCUR NEXT
6 | PARCEL 25,26,27 | SETTLED
7 | PARCEL 30 | COMPLAINT FILED, MEDIATION TO OCCUR NEXT
8 | PARCEL 33 | COMPLAINT FILED, MEDIATION TO OCCUR NEXT
9 | PARCEL 37 | COMPLAINT FILED, MEDIATION TO OCCUR NEXT
10 | PARCEL 54,55 | COMPLAINT FILED, MEDIATION TO OCCUR NEXT

## Slide 17
CONSTRUCTION/BETTERMENTS
www.indiantrail.org
STREETLIGHTS

## Slide 19
CONSTRUCTION/BETTERMENTS
www.indiantrail.org
FURNISHINGS

## Slide 20
CONSTRUCTION/BETTERMENTS
www.indiantrail.org
STREETLIGHTS = $650,000.00
FURNISHINGS = $60,000.00
SIGN RELOCATION = $220,000.00
ADDITIONAL FUND REQUEST = $930,000.00
NOTE: Tariffs (Electronic Drivers and LED Diodes)

## Slide 21
CONSTRUCTION/BETTERMENTS
www.indiantrail.org
Additional Utility Work (beyond Project limits)

## Slide 23
AMENDMENT TO ORDINANCE
www.indiantrail.org
ITEM DESCRIPTION | GRANT BREAKDOWN
DESIGN COORDINATION | $66,919.00*
R/W ACQUISITION ONGOING COSTS | $100,000.00
CONSTRUCTION | $903,081.00
STREETSCAPE AMENITIES | $930,000.00
TOTALS = | $2,000,000.00
*NOTE: ARBITRARY NUMBER VALUE

## Slide 24
AMENDED ORDINANCE
www.indiantrail.org
ITEM DESCRIPTION | PREVIOUS VALUES | $2.0 MIL BREAKDOWN | NEW VALUES
DESIGN | $983,081.00 | $66,919.00* | $1,050,000.00
RIGHT OF WAY | $2,500,000.00 | $100,000.00 | $2,600,000.00
CONSTRUCTION | $13,572,281.00 | $903,081.00 | $14,475,362.00
STREETSCAPE AMENITIES | $50,000.00 | $930,000.00 | $980,000.00
TOTALS = | $17,105,362 | $2,000,000 | $19,105,362
**NOTE: ARBITRARY NUMBER VALUE

## Slide 25
Project Budget
www.indiantrail.org
FUNDING SOURCES |  | FUNDING AMOUNTS
ATRIUM CONTRIBUTION |  | $1,174,000.00
TOWN CENTER CONTRIBUTION |  | $1,350,000.00
2021 STREET BOND |  | $1,142,000.00
GENERAL FUND |  | $438,385.00
CRTPO FUNDING |  | $7,950,977.00
NC DEPT. OF COMMERCE GRANT |  | $50,000.00
NC SCIF GRANT |  | $7,000,000.00
 | TOTAL: | $19,105,362.00

## Slide 26
IT Complete Street Update
www.indiantrail.org
Questions

## Slide 27
FEDERAL FUNDS BREAKDOWN
www.indiantrail.org
ITEM DESCRIPTION | PREVIOUS AWARDED FUNDS | NEWLY AWARDED FUNDS | TOTAL AVAILABLE FUNDS
RIGHT OF WAY | $1,509,000.00 | $330,400.00 | $1,839,400.00
CONSTRUCTION | $5,739,000.00 | $1,321,600.00 | $7,060,600.00
TOTALS = | $7,248,000 | $1,652,000 | $8,900,000
**IMPORTANT** - ADDITIONAL AGENCY LIABILITY = $723,000.00

## Slide 28
PROJECT ACTIVITIES
www.indiantrail.org
ITEM DESCRIPTION | 
ROADWAY | 
TRAFFIC SIGNALS | 
WATER AND SEWER | 
TRAFFIC CONTROL | 
4TH LEG OF ROUNDABOUT |